## Slide 1: Study to Support a Sustainable Algae Industry
CINEA/2023/OP/0006/SI2.906327
online
07th June 2024
ROHELINE VIHMAVARI OÜ

## Slide 2: Study Objectives
Algae as key pathway to addressing: food security, climate change mitigation, employment and waste-related issues
Project: understand the potential, risks, challenges to the development of a sustainable EU algae sector
6 distinct topics (work packages) > comprehensive picture of whether/how algae can support the objectives of the EU Green Deal
Picture: Seaweed growing on bottom of sea

## Slide 3: Work Plan
Year |  | 2024 |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  | 
Calendar | 14.1. | 14.2. | 14.3. | 14.4. | 14.5 | 14.6. | 14.7 | 14.8. | 14.9 | 14.10. | 14.11 | 14.12. | 14.1. | 14.2. | 14.3. | 14.4. | 14.5. | 14.6.
Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Work Packages 1-6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
literature research and data collection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
stakeholder consultations (interviews, surveys) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
analysis and synthesis of findings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
validation (stakeholder workshops) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
development of final reports |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
The final reports will seek to create new knowledge and concrete recommendations on how to move forward towards a sustainable algae industry in the EU.

## Slide 4: Work Package 1 Investigating the use of algae-based feed as a replacement of fish-based feed in EU aquaculture

## Slide 5: Objectives
Conduct a comprehensive investigation into the use of algae feed in the EU
Explore different approaches and methodologies for substituting fish-based feed with algae-based feed ingredients in aquaculture
Perform a forecast analysis for the potential replacement of fish-based feed with algae-based feed in the EU

## Slide 6: EU Algae Initiative
Project Work Package | EU Algae Communication Action from the European Commission
WP 1 on algae-based feed as replacement of fish-based feed in aquaculture | Action 7 - based on the good practices, feed indicators, and other relevant information: develop specific guidance to promote replacing fish-based feed with algae-based feed
Notes: - EU Agae Initiative promised 23 actions regarding algae (will be completed 2030)
Many of the listed actions will be fulfilled by ALIS
- ALIS plays a core role in the EU Algae Initiative

## Slide 7: Which Algae will we focus on?
  MACRO ALGAE MICRO ALGAE
  Saccharina - Chlorella
  Ulva - Nannochloropsis
  Palmaria palmata - Schizochytrium sp.
Picture: Palmaria palmata
Primary fish species utilized for fish feed (EU):
- European anchovy - European sardine - Atlantic herring

## Slide 8: Methodology
Output | Planned Content
1. Recommendations for replacing fish-based feed with algae-based alternatives | 1 - Current use & acceptance of algae based feed in aquaculture 2 - Analysis of different fish feed ingredients and mixtures (MCA) 3 - Recommendations processing and inclusion levels of algae
2. Assessment of methods and methodologies for replacing fish-based feed | 1 - EU & national regulations relevant to algae as feed 2 - Operational criteria for industry standards 3 - EU forage fish dependency ratio (FFDR) 4 - Recommendations Minimum blend-in targets EPA + DHA 5 - Recommendations high potential algae ingredients candidates 6 – Recommendations ALARA (as low as reasonably achievable) contaminants 7- Sustainable Finance Taxonomy
3. Forecast analysis for the replacement of fish-based feed by algae-based feed | 1 - Current total usage of fish-based feed ingredients in EU aquaculture 2 - Ratios of fish feed which could be replaced with algal-based feed 3 - Potential of algal-based feed to be used in current EU aquaculture
Output | Planned Content
1. Recommendations for replacing fish-based feed with algae-based alternatives | 1 - Current use & acceptance of algae-based feed in aquaculture 2 - Analysis of different fish feed ingredients and mixtures (MCA) 3 - Recommendations processing and inclusion levels of algae
2. Assessment of methods and methodologies for replacing fish-based feed | 1 - EU & national regulations relevant to algae as feed 2 - Operational criteria for industry standards 3 - EU forage fish dependency ratio (FFDR) 4 - Recommendations ALARA (as low as reasonabliy achivable) contaminats 5 - Recommendations Minimum blend-in targets EPA + DHA 6 – Recommendations high potential algae ingredients candidates 7- Sustainable Finance Taxonomy
3. Forecast analysis for the replacement of fish-based feed by algae-based feed | 1 - Current total usage of fish-based feed ingredients in EU aquaculture 2 - Ratios of fish feed which could be replaced with algal-based feed 3 - Potential of algal-based feed to be used in current EU aquaculture
Notes: All about algae feed itself & compare it to different feed (fish/plant/... based) -> nutritional composition + economic + environmental. + processing/inclusion levels
2.1 - Regulatory aspects -> mapping of regulations to give overview
  2.2 - Recom. on operational criteria/industry standards
  2.3 FFDR: (evolution from FIFO -> focus: utilization of wild fish in feeds due to ecological concerns)
  -> Nutritional requirements & optimal dietary composition for key European fish species. Recommendations for its adjustment. Assessment of the environmental impacts linked to the current FFDR in aquaculture.
  - …

## Slide 9: Methodology
Output | Planned Content
1. Recommendations for replacing fish-based feed with algae-based alternatives | 1 - Current use & acceptance of algae-based feed in aquaculture 2 - Analysis of different fish feed ingredients and mixtures (MCA) 3 - Recommendations processing and inclusion levels of algae
2. Assessment of methods and methodologies for replacing fish-based feed | 1 - EU & national regulations relevant to algae as feed 2 - Operational criteria for industry standards 3 - EU forage fish dependency ratio (FFDR) 4 - Recommendations ALARA (as low as reasonabliy achivable) contaminats 5 - Recommendations Minimum blend-in targets EPA + DHA 6 – Recommendations high potential algae ingredients candidates 7- Sustainable Finance Taxonomy
3. Forecast analysis for the replacement of fish-based feed by algae-based feed | 1 - Current total usage of fish-based feed ingredients in EU aquaculture 2 - Ratios of fish feed which could be replaced with algal-based feed 3 - Potential of algal-based feed to be used in current EU aquaculture
GET INVOLVED!
​ ​
tms@sustainable-projects.eu
Notes: We will follow data protection notice DPN of the European Commission - data will be anonymised (except for if you don’t if you want that)
If you want to get involved, we are happy to discuss the details

## Slide 10: Projects & Studies
Let us know, if you have more relevant studies/projects/papers to share!
​ ​
tms@sustainable-projects.eu

## Slide 11: How can I get Involved?
We need YOUR help!
NOW:
Information, Studies, Projects
You could help guiding us as a member of the task force
​ ​
tms@sustainable-projects.eu

## Slide 12: How can I get Involved?
Planned activities:
10 Interviews - with industry and associations (fish & fish feed producers)
  August/September 2024
Surveys (on FFDR assessment, incl. consumer safety, and blend-in targets)
  Autumn 2024
Workshop - with WG4 to validate results and develop recommendations
  December 2024
​ ​
tms@sustainable-projects.eu

## Slide 13: Slido Survey
Scan QR-Code with your phone
OR
Join at slido.com and enter #2912726
​ ​
tms@sustainable-projects.eu

## Slide 14: Thank you!
ROHELINE VIHMAVARI OÜ