## Objectives with EURA
WG-2 | Objectives | May 2023
O1 | Better market knowledge, industry contacts, investors mapping | Still ongoing
O2 | A listing of solutions to free the circulation of the goods (Novel food, Wastewater/manure regulation, Biofetilizers | Novel Food link with WG3 + need to combine outcomes of other subtasks to create the list
O3 | The reassessment of the equivalences regimes with countries outside Europe (and within) | need more inputs (other countries)
O4 | Creation of a European label of high-quality EU microalgae production | TBD
O5 | Criteria for certification of biomass quality for food, feed, nutraceutics, cosmetics, Biostimulants/Biofertilisers | TBD
O6 | Knowledge platform to steer cost-effective and sustainable production, including automatization | Good progress on circular economy systems
O7 | Knowledge platform to focus on the production systems | Starting document to improve

## Sub-task with contributors
Objective (EC) | sub-task name (WG2) | Contributors | Done May 2023 | Next step
O1 | Communication-Market | Arnaud Grisard / Sylvia Fluch | 1st draft document done | Need to focus more on Market (strain / market target / companies) the reste can be picked up by other sub-tasks => need jean paul reviews that part
O2 | Novel Food | Hywel Griffiths | Redirected to WG3 (Food) | Hywel must keep update on NAFF / promote platform ?
O3 | Biobanks (culture collections) | Jean Paul Cadroet / Monique Ras | Done (list of 34) | Wait for Seastrain first draft document to harmonise (by end of June) => contact Adrien
O3 | Communication / clarity | Sylvio Mangini (EU regulation) / Johanne Jelnes(nutrition) / Monique Ras (impact) | Sylvio with an overview of EU regulation on "Origin" | Need to focus message and connect to O5 (Silvio), Johanne ? And Monique inputs provided mid-june
O3 | Regulation versus countries | Boris Brulmann (Germany) | Overview on German regulation | Need more contribution from other countries => survey ? Connect with Silvio for the regulation ?
O3 | Online Forum/meeting for microalgae producers | Jean Paul Cadroet / Monique Ras |  | Decide When and Content/message
O4 | Labels | ?? |  | Identify who
O5 | Criteria for Certification | ?? |  | Identify who
O6 | Circular economy | Frédérick Ferey (CO2)/ Laura Monteiro (Wastewater) | Well advanced factsheet | Need meeting to define what is missing
O7 | Production systems | TBC | Use paragraphe of O1 document as start-off document | Need define contributor to progress