## Sheet1
Action | Description | Deadline | Who? | Achieved? | Note
1 | Open a JIRA issue on TWG6-8 implementation of INSPIRE Compliant CSW for clarification on requested services. | Ongoing | EMODnet Secretariat | EM-48 | Chemisty, Geology and Physics (https://monitor.emodnet.eu/resources?lang=en&resource_type=OGC%3ACSW)
2 | Open a JIRA issue on TWG6-10 to clarify which EMODnet Chemistry data products could be offered through OGC services (if not yet the case). | Ongoing | EMODnet Secretariat | EM-49 | NO webservices?
3 | TWG6-Action 11 Open JIRA issue and plan bilateral meetings to identify which Physics products could be offered through OGC services (if not yet the case). | Ongoing | EMODnet Secretariat | EM-50 | http://geoserver.emodnet-physics.eu/geoserver/web/wicket/bookmarkable/org.geoserver.web.demo.MapPreviewPage?1
4 | Prepare a document, or tutorial to show JIRA workflow on recording and tracking to email queries that come through Emodnet helpdesk. | End of June | EMODnet Secretariat | Done (Xiaoyu Doc) | This exists for EMODpace needs to be repurposed for EMODnet
5 | EMODnet Secretariat will prepare a service desk workflow/protocol for dealing with contact forms (from the Secretariat perspective) | End of June | EMODnet Secretariat | Done (Xiaoyu Doc) | This exists for EMODpace needs to be repurposed for EMODnet
6 | TWG6-Action 22 Provide email contact to Secretariat technical coordinator of the persons to be notified in case of down time of OGC services as recorded by monitor.emodnet.eu and other technical issues. | End May | Thematic portals | NO | But VLIZ have been andling this.
7 | TWG3-Action 1: Check integration of the Physics climatology data in the Central Portal geoviewer. Will be followed up in JIRA | Ongoing | VLIZ
| TWG3-Action 2: Physics to provide combined climatology products for European scale (not per sea basin) for integration in the viewer. Correct parameters to be sent to VLIZ to see if the integration can be done. Will be followed up in JIRA |  | Emodnet Physics | Yes | This seems to be done
9 | Each portal team will be invited in turn to give a presentation at the weekly EMODnet/DG MARE/EASME meeting. | Ongoing | EMODnet Secretariat/DG MARE/EASME | Done (Xiaoyu Doc)
10 | Open JIRA issue with Chemistry to follow up on the updates to the Data products for the European Atlas of the Seas. | Ongoing | EMODnet Secretariat/EMODnet Chemistry | Yes
11 | Open JIRA issue with Geology on updates to their products for the European Atlas of the Seas | Ongoing | EMODnet Secretariat/EMODnet Geology | pending new Jira
12 | The TWG agreed to use the INSPIRE validator tool (JRC). | Ongoing | EMODnet Secretariat + Portals | EM-56 | We discussed improving this tool with Bilbomatica
13 | Secretariat to evaluate if the GeoServer Monitoring extension API can be used to monitor web service traffic to the Thematic Portal GeoServers. Thematic portals are to enable the monitoring extension in their GeoServer and provide access to Secretariat upon request. This will be followed up in JIRA issue 7 | Ongoing | EMODnet Secretariat/All EMODnet thematic portals | em-57 | Where are we?
14 | Conor Delaney and Julie Auerbach (EMODnet Secretariat) to come back to coordinators to review how to improve monitoring of webpage visits. Which web page do they want to be indexed? | Early June | EMODnet Secretariat. (This is part of process to review to progress indicators) | Yes
15 | EMODnet Secretariat to come up with a standard list of institutions and to review what else can be standardised across the lots. | Early June | EMODnet Secretariat. (This is part of process to review to progress indicators) | Yes
16 | Conor Delaney and Julie Auerbach (EMODnet Secretariat) to look at ways to make indicator 1.1 more comparable across lots as part of their review of the progress indicators. | Early June | EMODnet Secretariat. (This is part of process to review to progress indicators) | Yes
17 | Progress indicator 1.2 will be reviewed with coordinators | Early June | EMODnet Secretariat as part of indicator review process | Yes
18 | All the portals should open the indicators and dashboard to public. | Ongoing | Thematic portals & Secretariat | waiting for deployment to VLIZ
19 | Follow up on the correct functionality of the dashboard. | Ongoing | Secretariat | Yes
20 | Make a tutorial on how to use the progress indicator dashboard. | End May | All EMODnet thematic portals and Trust-IT | Yes
21 | Upload and provide links to reports are requested from thematic lots to upload to Central Portal. | Ongoing | Portals and Secretariat | Done (Xiaoyu Doc)