## Slide 1
Coastal Mapping
Final meeting
SHOM
gael.morvan@shom.fr

## Slide 2: Genesis
  Memorandum of Understanding (MoU) – 23 April 2012
    Framework for interaction between the EC and the IHO
  Creation of the IHO-EU Network WG (June 2013)
    Decided at the 5th IHO IRCC meeting
    Developed and chaired by France
  Development of a Joint European Coastal Mapping Programme (JECMaP) within this WG
  Concurrently, CPMR work on data knowledge for the management of coastal areas
  On-going EMODnet projects

## Slide 3: Service contract
Signed by SHOM on 29 May 2015
Signed by EASME on 26 June 2015
3-year duration with 2 periods of 18 months:
  Production period from 26 June 2015 to 26 Dec. 2016
  Maintenance period from 26 Dec. 2016 to 26 June 2018

## Slide 4: Objectives
  Assess the current availability of digital coastal maps in the EU
  Disseminate this information by EMODnet
  Share experience of coastal mapping in the EU
  Develop standards for best practices
  Propose how a future JECMAP could operate

## Slide 5: Deliverables
Every 2 months: progress report
26 Dec. 2015: first version of portal on-line
26 March 2016: interim report
26 Dec. 2016:
  final version of portal on-line
  final report
  executive summary of final report
Around Feb. 2017 : stakeholder workshop
26 June 2018 : maintenance report

## Slide 6: Consortium
Hydrographic offices :
FRANCE – BELGIUM – GERMANY – GREECE – IRELAND – ITALY – LATVIA – NORWAY – PORTUGAL – SLOVENIA – SWEDEN
Regions :
CPMR – Regione Lazio
Public Bodies :
ISPRA – RWS - GeoEcomar – DDNI
IT company :
Worldline

## Slide 7: Organisation

## Slide 8: Project group meetings
  WP1 & KO meetings (23-24/06/2015, St Mandé)
  Specification meeting (21-22/10/2015, Ostend)
  Portal meeting (1-2/12/2015, Bezons)
  Algorithm meeting (2-3-4/03/2016, Roma)
  Interim meeting (7-8/06/2016, Stockholm)
  Progress meeting (14-15/09/2016, Dublin)
  Final meeting (8/12/2016, Brussels)
  Stakeholder meeting (Feb. 2017, Brussels)

## Slide 9: Side meetings
  EMODnet steering committees
  EMODnet-INSPIRE workshops
  EMODnet Technical WG meetings
  Seminar at JRC
  (Last) MODEG meeting
  EMODnet Bathymetry progress meetings
  EMODnet-MSFD coordination meetings
  IENWG meetings
  MPMSEG meeting
  Bologna Charter Coordination Board
  EUREF 2016 symposium
  Italian National Table on Coastal Erosion
  …

## Slide 10: Thank you!